## Task Breakdown
Task Breakdown
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Create user stories list | 2025-03-14 | 2025-03-14
2 | Develop design guide (logo, fonts, colors) | 2025-03-14 | 2025-03-14
3 | Create high-fidelity wireframes | 2025-03-14 | 2025-03-14
4 | Write User-Centered Analysis and Design Documentation | 2025-03-14 | 2025-03-14
5 | Build first webpage (HTML & CSS) | 2025-03-15 | 2025-03-15
6 | Implement navigation menu and footer | 2025-03-15 | 2025-03-15
7 | Add key content sections (hours, fares, history, contact info, etc.) | 2025-03-15 | 2025-03-15
8 | Plan JavaScript functions and interactions | 2025-03-15 | 2025-03-15
9 | Integrate DOM manipulation or event handlers | 2025-03-19 | 2025-03-19
10 | Implement Google Maps API for directions | 2025-03-20 | 2025-03-19
11 | Add jQuery feature (carousel, interactive elements, etc.) | 2025-03-21 | 2025-03-22
12 | User testing and feedback collection | 2025-03-24 | 2025-03-24
13 | Revise based on feedback and finalize design | 2025-03-26 | 2025-03-25
14 | Submit final website and documentation | 2025-03-30 | 2025-03-30
...